## Test Plan
Field | Value
Project Name | Manual Testing Project – Web (E‑commerce Demo)
Application Under Test (AUT) | E‑commerce Web App (Demo)
URL / App Package | https://practicesoftwaretesting.com/
Scope (In-Scope) | Login, Search, Product Details, Add to Cart, Cart, Checkout (UI validations only)
Out of Scope | Payments gateway integration, Performance/Load, Security testing
Test Types | Smoke, Functional, Regression, UI/UX checks, Basic Compatibility
Environments | Windows 10/11 + Chrome/Firefox; Android Chrome (optional)
Entry Criteria | Build deployed, basic smoke passes, test data available
Exit Criteria | All high/critical defects fixed or deferred with sign-off; test coverage >= 95%
Test Data Strategy | Use dummy accounts; seed products/categories; edge cases documented
Risks & Mitigations | Environment instability – Plan daily smoke; Test data leaks – Use dummy data
Tools | MS Excel, JIRA/Bugzilla (optional), Screenshot tool, ADB/CLI (optional)
Roles & Responsibilities | Ferina
Reporting Cadence | Daily status update, end-of-cycle Test Summary Report
Approvals | Tester, Reviewer (sign-off)
Version | v1.0 - 2025-10-17

## Test Cases
TC ID | Module | Title | Preconditions | Steps | Test Data | Expected Result | Priority | Type | Status | Actual Result | Evidence | Bug ID
TC-LOGIN-001 | Login | Login with valid credentials | User is registered; Browser on Login page | 1) Enter valid email 2) Enter valid password 3) Click Login | email: user@test.com, pwd: P@ssw0rd | User lands on Dashboard/Home; username visible | High | Functional, Smoke | Pass
TC-SEARCH-002 | Search | Search existing product by exact name | User on Home page | 1) Type product name in search 2) Press Enter | Query: 'Wireless Mouse' | Results list shows 'Wireless Mouse' as first or relevant item | Medium | Functional | Pass
TC-CART-003 | Cart | Add product to cart from PDP | User on Product Detail Page | 1) Click 'Add to Cart' | SKU: WM-123 | Cart count increments; success toast appears | High | Functional, Regression | Pass
TC-CHECKOUT-004 | Checkout | Checkout with COD (positive flow) | Cart has 1 item; User logged in | 1) Go to Cart 2) Click Checkout 3) Fill address 4) Choose COD 5) Place Order | Address: valid; Payment: COD | Order confirmation page with Order ID | High | Functional | Pass

## Execution Log
Run ID | Date | Build | Tester | TC ID | Result | Notes
RUN-001 | 2025-10-17 | v1.0.0 | Ferina | TC-LOGIN-001 | Pass | Working as expected

## Defect Log
Bug ID | Title | Module | Severity | Priority | Environment | Build | Reported By | Assigned To | Status | Steps to Reproduce | Expected Result | Actual Result | Attachments | Created On
BUG-001 | Error toast overlaps login button on small viewport | Login | Medium | High | Windows 11, Chrome 124 | v1.0.0 | Ferina |  | Closed | 1) Open Login on 360px width 2) Enter invalid password 3) Click Login | Error message readable, layout intact | Toast overlaps button, blocking interaction | login_overlap.png | 2025-10-17

## RTM
Requirement ID | Requirement Description | Test Case IDs | Coverage | Defects Linked
REQ-LOGIN-01 | System shall allow registered users to login using email and password | TC-LOGIN-001, TC-LOGIN-005 | Covered | BUG-001 (layout)
REQ-CHECKOUT-02 | System shall enable checkout with COD option | TC-CHECKOUT-004 | Covered

## Test Summary
Metric | Value
Total Test Cases | 25
Executed | 25
Passed | 22
Failed | 0
Blocked | 0
Pass % | 0
Fail % | 0
Total Defects | 1
Critical | 0
High | 0
Medium | 1
Low | 0